**PROJECT MANAGEMENT**

**Learning Outcome 2: ACTIVITY 3**

**PAIRS ACTIVITY**

**Blitz Alloys project part 3**

The project is scheduled to commence on Monday 5 April. All days quoted are working days (i.e. 5 days equates to 1 week as weekends will not be worked). Ignore the possibility of any holidays.

The Chief Executive is planning to visit the new site to evaluate the change in working practices (on the Thursday during the week after the project has finished).

Using the calendar shown below identify the date of the visit.

There is some concern about the limited time allowed for task C. How many days (if any) could task C be delayed without delaying the completion of the project?

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|

|  |
| --- |
| [**Apr**](http://my.calendars.net/bigdemo/d01/04/2004?authenticate=&style=B&display=M&positioning=A) |
| S | M | T | W | T | F | S |
|  |  |  |  | [1](http://my.calendars.net/bigdemo/d01/04/2004?authenticate=&style=B&display=D&positioning=A) | [2](http://my.calendars.net/bigdemo/d02/04/2004?authenticate=&style=B&display=D&positioning=A) | [3](http://my.calendars.net/bigdemo/d03/04/2004?authenticate=&style=B&display=D&positioning=A) |
| [4](http://my.calendars.net/bigdemo/d04/04/2004?authenticate=&style=B&display=D&positioning=A) | [5](http://my.calendars.net/bigdemo/d05/04/2004?authenticate=&style=B&display=D&positioning=A) | [6](http://my.calendars.net/bigdemo/d06/04/2004?authenticate=&style=B&display=D&positioning=A) | [7](http://my.calendars.net/bigdemo/d07/04/2004?authenticate=&style=B&display=D&positioning=A) | [8](http://my.calendars.net/bigdemo/d08/04/2004?authenticate=&style=B&display=D&positioning=A) | [9](http://my.calendars.net/bigdemo/d09/04/2004?authenticate=&style=B&display=D&positioning=A) | [10](http://my.calendars.net/bigdemo/d10/04/2004?authenticate=&style=B&display=D&positioning=A) |
| [11](http://my.calendars.net/bigdemo/d11/04/2004?authenticate=&style=B&display=D&positioning=A) | [12](http://my.calendars.net/bigdemo/d12/04/2004?authenticate=&style=B&display=D&positioning=A) | [13](http://my.calendars.net/bigdemo/d13/04/2004?authenticate=&style=B&display=D&positioning=A) | [14](http://my.calendars.net/bigdemo/d14/04/2004?authenticate=&style=B&display=D&positioning=A) | [15](http://my.calendars.net/bigdemo/d15/04/2004?authenticate=&style=B&display=D&positioning=A) | [16](http://my.calendars.net/bigdemo/d16/04/2004?authenticate=&style=B&display=D&positioning=A) | [17](http://my.calendars.net/bigdemo/d17/04/2004?authenticate=&style=B&display=D&positioning=A) |
| [18](http://my.calendars.net/bigdemo/d18/04/2004?authenticate=&style=B&display=D&positioning=A) | [19](http://my.calendars.net/bigdemo/d19/04/2004?authenticate=&style=B&display=D&positioning=A) | [20](http://my.calendars.net/bigdemo/d20/04/2004?authenticate=&style=B&display=D&positioning=A) | [21](http://my.calendars.net/bigdemo/d21/04/2004?authenticate=&style=B&display=D&positioning=A) | [22](http://my.calendars.net/bigdemo/d22/04/2004?authenticate=&style=B&display=D&positioning=A) | [23](http://my.calendars.net/bigdemo/d23/04/2004?authenticate=&style=B&display=D&positioning=A) | [24](http://my.calendars.net/bigdemo/d24/04/2004?authenticate=&style=B&display=D&positioning=A) |
| [25](http://my.calendars.net/bigdemo/d25/04/2004?authenticate=&style=B&display=D&positioning=A) | [26](http://my.calendars.net/bigdemo/d26/04/2004?authenticate=&style=B&display=D&positioning=A) | [27](http://my.calendars.net/bigdemo/d27/04/2004?authenticate=&style=B&display=D&positioning=A) | [28](http://my.calendars.net/bigdemo/d28/04/2004?authenticate=&style=B&display=D&positioning=A) | [29](http://my.calendars.net/bigdemo/d29/04/2004?authenticate=&style=B&display=D&positioning=A) | [30](http://my.calendars.net/bigdemo/d30/04/2004?authenticate=&style=B&display=D&positioning=A) |  |
|  |  |  |  |  |  |  |

 |

|  |
| --- |
| [**May**](http://my.calendars.net/bigdemo/d01/05/2004?authenticate=&style=B&display=M&positioning=A) |
| S | M | T | W | T | F | S |
|  |  |  |  |  |  | [1](http://my.calendars.net/bigdemo/d01/05/2004?authenticate=&style=B&display=D&positioning=A) |
| [2](http://my.calendars.net/bigdemo/d02/05/2004?authenticate=&style=B&display=D&positioning=A) | [3](http://my.calendars.net/bigdemo/d03/05/2004?authenticate=&style=B&display=D&positioning=A) | [4](http://my.calendars.net/bigdemo/d04/05/2004?authenticate=&style=B&display=D&positioning=A) | [5](http://my.calendars.net/bigdemo/d05/05/2004?authenticate=&style=B&display=D&positioning=A) | [6](http://my.calendars.net/bigdemo/d06/05/2004?authenticate=&style=B&display=D&positioning=A) | [7](http://my.calendars.net/bigdemo/d07/05/2004?authenticate=&style=B&display=D&positioning=A) | [8](http://my.calendars.net/bigdemo/d08/05/2004?authenticate=&style=B&display=D&positioning=A) |
| [9](http://my.calendars.net/bigdemo/d09/05/2004?authenticate=&style=B&display=D&positioning=A) | [10](http://my.calendars.net/bigdemo/d10/05/2004?authenticate=&style=B&display=D&positioning=A) | [11](http://my.calendars.net/bigdemo/d11/05/2004?authenticate=&style=B&display=D&positioning=A) | [12](http://my.calendars.net/bigdemo/d12/05/2004?authenticate=&style=B&display=D&positioning=A) | [13](http://my.calendars.net/bigdemo/d13/05/2004?authenticate=&style=B&display=D&positioning=A) | [14](http://my.calendars.net/bigdemo/d14/05/2004?authenticate=&style=B&display=D&positioning=A) | [15](http://my.calendars.net/bigdemo/d15/05/2004?authenticate=&style=B&display=D&positioning=A) |
| [16](http://my.calendars.net/bigdemo/d16/05/2004?authenticate=&style=B&display=D&positioning=A) | [17](http://my.calendars.net/bigdemo/d17/05/2004?authenticate=&style=B&display=D&positioning=A) | [18](http://my.calendars.net/bigdemo/d18/05/2004?authenticate=&style=B&display=D&positioning=A) | [19](http://my.calendars.net/bigdemo/d19/05/2004?authenticate=&style=B&display=D&positioning=A) | [20](http://my.calendars.net/bigdemo/d20/05/2004?authenticate=&style=B&display=D&positioning=A) | [21](http://my.calendars.net/bigdemo/d21/05/2004?authenticate=&style=B&display=D&positioning=A) | [22](http://my.calendars.net/bigdemo/d22/05/2004?authenticate=&style=B&display=D&positioning=A) |
| [23](http://my.calendars.net/bigdemo/d23/05/2004?authenticate=&style=B&display=D&positioning=A) | [24](http://my.calendars.net/bigdemo/d24/05/2004?authenticate=&style=B&display=D&positioning=A) | [25](http://my.calendars.net/bigdemo/d25/05/2004?authenticate=&style=B&display=D&positioning=A) | [26](http://my.calendars.net/bigdemo/d26/05/2004?authenticate=&style=B&display=D&positioning=A) | [27](http://my.calendars.net/bigdemo/d27/05/2004?authenticate=&style=B&display=D&positioning=A) | [28](http://my.calendars.net/bigdemo/d28/05/2004?authenticate=&style=B&display=D&positioning=A) | [29](http://my.calendars.net/bigdemo/d29/05/2004?authenticate=&style=B&display=D&positioning=A) |
| [30](http://my.calendars.net/bigdemo/d30/05/2004?authenticate=&style=B&display=D&positioning=A) | [31](http://my.calendars.net/bigdemo/d31/05/2004?authenticate=&style=B&display=D&positioning=A) |  |  |  |  |  |

 |

|  |
| --- |
| [**Jun**](http://my.calendars.net/bigdemo/d01/06/2004?authenticate=&style=B&display=M&positioning=A) |
| S | M | T | W | T | F | S |
|  |  | [1](http://my.calendars.net/bigdemo/d01/06/2004?authenticate=&style=B&display=D&positioning=A) | [2](http://my.calendars.net/bigdemo/d02/06/2004?authenticate=&style=B&display=D&positioning=A) | [3](http://my.calendars.net/bigdemo/d03/06/2004?authenticate=&style=B&display=D&positioning=A) | [4](http://my.calendars.net/bigdemo/d04/06/2004?authenticate=&style=B&display=D&positioning=A) | [5](http://my.calendars.net/bigdemo/d05/06/2004?authenticate=&style=B&display=D&positioning=A) |
| [6](http://my.calendars.net/bigdemo/d06/06/2004?authenticate=&style=B&display=D&positioning=A) | [7](http://my.calendars.net/bigdemo/d07/06/2004?authenticate=&style=B&display=D&positioning=A) | [8](http://my.calendars.net/bigdemo/d08/06/2004?authenticate=&style=B&display=D&positioning=A) | [9](http://my.calendars.net/bigdemo/d09/06/2004?authenticate=&style=B&display=D&positioning=A) | [10](http://my.calendars.net/bigdemo/d10/06/2004?authenticate=&style=B&display=D&positioning=A) | [11](http://my.calendars.net/bigdemo/d11/06/2004?authenticate=&style=B&display=D&positioning=A) | [12](http://my.calendars.net/bigdemo/d12/06/2004?authenticate=&style=B&display=D&positioning=A) |
| [13](http://my.calendars.net/bigdemo/d13/06/2004?authenticate=&style=B&display=D&positioning=A) | [14](http://my.calendars.net/bigdemo/d14/06/2004?authenticate=&style=B&display=D&positioning=A) | [15](http://my.calendars.net/bigdemo/d15/06/2004?authenticate=&style=B&display=D&positioning=A) | [16](http://my.calendars.net/bigdemo/d16/06/2004?authenticate=&style=B&display=D&positioning=A) | [17](http://my.calendars.net/bigdemo/d17/06/2004?authenticate=&style=B&display=D&positioning=A) | [18](http://my.calendars.net/bigdemo/d18/06/2004?authenticate=&style=B&display=D&positioning=A) | [19](http://my.calendars.net/bigdemo/d19/06/2004?authenticate=&style=B&display=D&positioning=A) |
| [20](http://my.calendars.net/bigdemo/d20/06/2004?authenticate=&style=B&display=D&positioning=A) | [21](http://my.calendars.net/bigdemo/d21/06/2004?authenticate=&style=B&display=D&positioning=A) | [22](http://my.calendars.net/bigdemo/d22/06/2004?authenticate=&style=B&display=D&positioning=A) | [23](http://my.calendars.net/bigdemo/d23/06/2004?authenticate=&style=B&display=D&positioning=A) | [24](http://my.calendars.net/bigdemo/d24/06/2004?authenticate=&style=B&display=D&positioning=A) | [25](http://my.calendars.net/bigdemo/d25/06/2004?authenticate=&style=B&display=D&positioning=A) | [26](http://my.calendars.net/bigdemo/d26/06/2004?authenticate=&style=B&display=D&positioning=A) |
| [27](http://my.calendars.net/bigdemo/d27/06/2004?authenticate=&style=B&display=D&positioning=A) | [28](http://my.calendars.net/bigdemo/d28/06/2004?authenticate=&style=B&display=D&positioning=A) | [29](http://my.calendars.net/bigdemo/d29/06/2004?authenticate=&style=B&display=D&positioning=A) | [30](http://my.calendars.net/bigdemo/d30/06/2004?authenticate=&style=B&display=D&positioning=A) |  |  |  |
|  |  |  |  |  |  |  |

 |